## Sheet1
Week | Task | Task Details | Status | Completed Date | Planned Completion Date
Week 1 | Upload Survey Questions | Upload all existing survey questions into the system | Pending |  | 2025-02-05
Week 1 | Improve Survey Analytics UI | Show category-wise and individual respondent scores | Pending |  | 2025-02-06
Week 1 | Progress Tracking in Survey | Show question numbers while taking survey | Pending |  | 2025-02-07
Week 1 | Start Survey Saving Feature | Allow respondents to save incomplete surveys | Pending |  | 2025-02-10
Week 1 | Ensure Survey Resume Feature | Store saved responses and allow resumption | Pending |  | 2025-02-11
Week 2 | Survey Instance Validity | Add expiration dates to survey instances | Pending |  | 2025-02-12
Week 2 | Enforce Survey Expiry | Prevent submissions after survey validity ends | Pending |  | 2025-02-13
Week 2 | Stop Accepting Responses | Allow admins to manually stop survey responses | Pending |  | 2025-02-14
Week 2 | Hide Survey Form | Ensure UI hides form after stopping responses | Pending |  | 2025-02-17
Week 2 | Control Score Visibility | Hide scores until survey instance is closed | Pending |  | 2025-02-18
Week 2 | Test Email Reminders | Ensure reminders work before survey expiry | Pending |  | 2025-02-19
Week 2 | Final Testing & Bug Fixes | Test and fix new feature issues | Pending |  | 2025-02-20
Week 3 | Implement Survey Dashboard | Admin dashboard with survey statuses and engagement | Pending |  | 2025-02-21
Week 3 | Survey Engagement Metrics | Show survey instance completion rates | Pending |  | 2025-02-24
Week 3 | Enable CSV Export | Allow admins to export survey results | Pending |  | 2025-02-25
Week 3 | Optimize DB Queries | Improve survey data retrieval speed | Pending |  | 2025-02-26
Week 3 | Improve UI Styling | Enhance user experience and layout | Pending |  | 2025-02-27
Week 3 | System-Wide Security Test | Ensure access controls are correct | Pending |  | 2025-02-28
Week 3 | Clone Survey Feature | Allow users to duplicate surveys easily | Pending |  | 2025-02-05
Week 4 | Bulk Question Editing | Enable batch editing for survey questions | Pending |  | 2025-02-06
Week 4 | Allow Editing of Surveys | Enable admins to edit survey questions | Pending |  | 2025-02-07
Week 4 | Basic AI Insights | Suggest improvements based on survey scores | Pending |  | 2025-02-10
Week 4 | Improve AI Suggestions | Fine-tune survey recommendations | Pending |  | 2025-02-11
Week 4 | Email Notifications for Incomplete Surveys | Send reminders for unfinished surveys | Pending |  | 2025-02-12
Week 4 | Add Text Area Questions | Allow text-based responses in surveys | Pending |  | 2025-02-13
Week 4 | Implement Text Analysis | Analyze text responses for patterns | Pending |  | 2025-02-14
Week 5 | Optimize Mobile UI | Ensure smooth survey experience on mobile | Pending |  | 2025-02-17
Week 5 | Mobile Performance Testing | Check responsiveness on different devices | Pending |  | 2025-02-18
Week 5 | Security Audit | Ensure no unauthorized data access | Pending |  | 2025-02-19
Week 5 | Survey Performance Analytics | Track time taken per question | Pending |  | 2025-02-20
Week 5 | Final UI Enhancements | Fix layout and responsiveness issues | Pending |  | 2025-02-21
Week 5 | Test Large Surveys | Check system stability with large surveys | Pending |  | 2025-02-24
Week 5 | Fix Major Bugs | Resolve issues found during testing | Pending |  | 2025-02-25
Week 6 | Ensure Proper Survey Indexing | Optimize MongoDB indexes for faster queries | Pending |  | 2025-02-26
Week 6 | Industry & Category Filtering | Allow analytics based on industry selection | Pending |  | 2025-02-27
Week 6 | Optimize Email System | Ensure bulk emails don’t get marked as spam | Pending |  | 2025-02-28
Week 6 | Final Survey Completion Reminders | Last-minute reminders to respondents | Pending |  | 2025-02-05
Week 6 | Final Bug Fixes | Resolve remaining issues before feature freeze | Pending |  | 2025-02-06
Week 6 | Feature Freeze | Lock features and start final testing | Pending |  | 2025-02-07
Week 6 | Final Pre-March Testing | Ensure everything works smoothly | Pending |  | 2025-02-10
Week 7 | Full System Testing | Check all workflows for stability | Pending |  | 2025-02-11
Week 7 | Implement Extra Security Measures | Enhance access controls | Pending |  | 2025-02-12
Week 7 | Final Review of Survey Workflows | Ensure smooth user journey | Pending |  | 2025-02-13
Week 7 | Multi-User Testing | Check for performance issues with concurrent users | Pending |  | 2025-02-14
Week 7 | Fix Load Testing Issues | Resolve any problems found | Pending |  | 2025-02-17
Week 7 | Prepare for Beta Testing | Identify users for testing | Pending |  | 2025-02-18
Week 7 | Feedback Collection Mechanism | Allow users to leave feedback on surveys | Pending |  | 2025-02-19
Week 7 | Final Mobile Optimization | Ensure surveys work flawlessly on mobile | Pending |  | 2025-02-20
Week 7 | Stress Testing | Test system under heavy load | Pending |  | 2025-02-21
Week 7 | Security Patches | Implement final security improvements | Pending |  | 2025-02-24
Week 7 | Final System Test Before Break | Ensure everything is ready | Pending |  | 2025-02-25
Week 7 | Documentation | Write internal documentation for admins | Pending |  | 2025-02-26
Week 7 | Final Bug Fixes & Feature Lock | Fix last-minute issues | Pending |  | 2025-02-27
Week 8 | Post-Break System Review | Check for any unexpected issues | Pending |  | 2025-02-28
Week 8 | Final Launch & Internal Rollout | Deploy system for usage | Pending |  | 2025-02-05