## Sheet1
Week | Date | Task | Task Details | Status | Completed Date
Week 1 | Jan 20 | Implement Industry Field | Add industry field in company schema | Pending
Week 1 | Jan 21 | Improve Industry UI | Allow users to select industry during signup | Pending
Week 1 | Jan 22 | Upload Survey Questions | Upload all existing survey questions into the system | Pending
Week 1 | Jan 23 | Improve Survey Analytics UI | Show category-wise and individual respondent scores | Pending
Week 1 | Jan 24 | Progress Tracking in Survey | Show question numbers while taking survey | Pending
Week 1 | Jan 25 | Start Survey Saving Feature | Allow respondents to save incomplete surveys | Pending
Week 1 | Jan 26 | Ensure Survey Resume Feature | Store saved responses and allow resumption | Pending
Week 2 | Jan 27 | Survey Instance Validity | Add expiration dates to survey instances | Pending
Week 2 | Jan 28 | Enforce Survey Expiry | Prevent submissions after survey validity ends | Pending
Week 2 | Jan 29 | Stop Accepting Responses | Allow admins to manually stop survey responses | Pending
Week 2 | Jan 30 | Hide Survey Form | Ensure UI hides form after stopping responses | Pending
Week 2 | Jan 31 | Control Score Visibility | Hide scores until survey instance is closed | Pending
Week 2 | Feb 1 | Test Email Reminders | Ensure reminders work before survey expiry | Pending
Week 2 | Feb 2 | Final Testing & Bug Fixes | Test and fix new feature issues | Pending
Week 3 | Feb 3 | Implement Survey Dashboard | Admin dashboard with survey statuses and engagement | Pending
Week 3 | Feb 4 | Survey Engagement Metrics | Show survey instance completion rates | Pending
Week 3 | Feb 5 | Enable CSV Export | Allow admins to export survey results | Pending
Week 3 | Feb 6 | Optimize DB Queries | Improve survey data retrieval speed | Pending
Week 3 | Feb 7 | Improve UI Styling | Enhance user experience and layout | Pending
Week 3 | Feb 8 | System-Wide Security Test | Ensure access controls are correct | Pending
Week 3 | Feb 9 | Clone Survey Feature | Allow users to duplicate surveys easily | Pending
Week 4 | Feb 10 | Bulk Question Editing | Enable batch editing for survey questions | Pending
Week 4 | Feb 11 | Allow Editing of Surveys | Enable admins to edit survey questions | Pending
Week 4 | Feb 12 | Basic AI Insights | Suggest improvements based on survey scores | Pending
Week 4 | Feb 13 | Improve AI Suggestions | Fine-tune survey recommendations | Pending
Week 4 | Feb 14 | Email Notifications for Incomplete Surveys | Send reminders for unfinished surveys | Pending
Week 4 | Feb 15 | Add Text Area Questions | Allow text-based responses in surveys | Pending
Week 4 | Feb 16 | Implement Text Analysis | Analyze text responses for patterns | Pending
Week 5 | Feb 17 | Optimize Mobile UI | Ensure smooth survey experience on mobile | Pending
Week 5 | Feb 18 | Mobile Performance Testing | Check responsiveness on different devices | Pending
Week 5 | Feb 19 | Security Audit | Ensure no unauthorized data access | Pending
Week 5 | Feb 20 | Survey Performance Analytics | Track time taken per question | Pending
Week 5 | Feb 21 | Final UI Enhancements | Fix layout and responsiveness issues | Pending
Week 5 | Feb 22 | Test Large Surveys | Check system stability with large surveys | Pending
Week 5 | Feb 23 | Fix Major Bugs | Resolve issues found during testing | Pending
Week 6 | Feb 24 | Ensure Proper Survey Indexing | Optimize MongoDB indexes for faster queries | Pending
Week 6 | Feb 25 | Industry & Category Filtering | Allow analytics based on industry selection | Pending
Week 6 | Feb 26 | Optimize Email System | Ensure bulk emails don’t get marked as spam | Pending
Week 6 | Feb 27 | Final Survey Completion Reminders | Last-minute reminders to respondents | Pending
Week 6 | Feb 28 | Final Bug Fixes | Resolve remaining issues before feature freeze | Pending
Week 6 | Mar 1 | Feature Freeze | Lock features and start final testing | Pending
Week 6 | Mar 2 | Final Pre-March Testing | Ensure everything works smoothly | Pending
Week 7 | Mar 3 | Full System Testing | Check all workflows for stability | Pending
Week 7 | Mar 4 | Implement Extra Security Measures | Enhance access controls | Pending
Week 7 | Mar 5 | Final Review of Survey Workflows | Ensure smooth user journey | Pending
Week 7 | Mar 6 | Multi-User Testing | Check for performance issues with concurrent users | Pending
Week 7 | Mar 7 | Fix Load Testing Issues | Resolve any problems found | Pending
Week 7 | Mar 8 | Prepare for Beta Testing | Identify users for testing | Pending
Week 7 | Mar 9 | Feedback Collection Mechanism | Allow users to leave feedback on surveys | Pending
Week 7 | Mar 10 | Final Mobile Optimization | Ensure surveys work flawlessly on mobile | Pending
Week 7 | Mar 11 | Stress Testing | Test system under heavy load | Pending
Week 7 | Mar 12 | Security Patches | Implement final security improvements | Pending
Week 7 | Mar 13 | Final System Test Before Break | Ensure everything is ready | Pending
Week 7 | Mar 14 | Documentation | Write internal documentation for admins | Pending
Week 7 | Mar 15 | Final Bug Fixes & Feature Lock | Fix last-minute issues | Pending
Week 8 | Mar 30 | Post-Break System Review | Check for any unexpected issues | Pending
Week 8 | Mar 31 | Final Launch & Internal Rollout | Deploy system for usage | Pending