## List
Week | Date | Task | Task Details | Status | Completed Date | Comments | 33.93%
Week 1 | 2025-01-20 | Implement Industry Field | Add industry field in account schema | Done | 2025-01-20
Week 1 | 2025-01-21 | Improve Industry UI | Allow users to select industry during signup | Done | 2025-01-20
Week 1 | 2025-01-22 | Upload Survey Questions | Upload all existing survey questions into the system | Done | 2025-01-20
Week 1 | 2025-01-23 | Improve Survey Analytics UI | Show category-wise and individual respondent scores | Done | 2025-01-21 | I don’t want to show individual respondent scores
Week 1 | 2025-01-24 | Progress Tracking in Survey | Show question numbers while taking survey | Done | 2025-01-21
Week 1 | 2025-01-25 | Start Survey Saving Feature | Allow respondents to save incomplete surveys | Done | 2025-01-21
Week 1 | 2025-01-26 | Ensure Survey Resume Feature | Store saved responses and allow resumption | Done | 2025-01-21
Week 2 | 2025-01-27 | Survey Instance Validity | Add expiration dates to survey instances | Done | 2025-01-22
Week 2 | 2025-01-28 | Enforce Survey Expiry | Prevent submissions after survey validity ends | Done | 2025-01-22
Week 2 | 2025-01-29 | Stop Accepting Responses | Allow admins to manually stop survey responses | Done | 2025-01-22
Week 2 | 2025-01-30 | Hide Survey Form | Ensure UI hides form after stopping responses | Done | 2025-01-22 | Shows a message
Week 2 | 2025-01-31 | Control Score Visibility | Hide scores until survey instance is closed | Done | 2025-01-22
Week 2 | 2025-02-01 | Test Email Reminders | Ensure reminders work before survey expiry | Done | 2025-01-22
Week 2 | 2025-02-01 | Edit Survey | Edit survey instance details | Done | 2025-01-22
Week 2 | 2025-02-02 | Final Testing & Bug Fixes | Test and fix new feature issues | Done | 2025-01-22
Week 3 | 2025-02-03 | Implement Survey Dashboard | Admin dashboard with survey statuses and engagement | Pending
Week 3 | 2025-02-04 | Survey Engagement Metrics | Show survey instance completion rates | Done | 2025-01-24
Week 3 | 2025-02-05 | Enable CSV Export | Allow admins to export survey results | Pending
Week 3 | 2025-02-06 | Optimize DB Queries | Improve survey data retrieval speed | Pending
Week 3 | 2025-02-07 | Improve UI Styling | Enhance user experience and layout | Pending
Week 3 | 2025-02-08 | System-Wide Security Test | Ensure access controls are correct | Pending
Week 3 | 2025-02-09 | Clone Survey Feature | Allow users to duplicate surveys easily | Pending |  | Not planning for MVP
Week 4 | 2025-02-10 | Bulk Question Editing | Enable batch editing for survey questions | Not planned |  | Not planning for MVP
Week 4 | 2025-02-11 | Allow Editing of Surveys | Enable admins to edit survey questions | Not planned |  | Not planning for MVP
Week 4 | 2025-02-12 | Basic AI Insights | Suggest improvements based on survey scores | Pending
Week 4 | 2025-02-13 | Improve AI Suggestions | Fine-tune survey recommendations | Pending
Week 4 | 2025-02-14 | Email Notifications for Incomplete Surveys | Send reminders for unfinished surveys | Done
Week 4 | 2025-02-15 | Add Text Area Questions | Allow text-based responses in surveys | Done
Week 4 | 2025-02-16 | Implement Text Analysis | Analyze text responses for patterns | Done | 2025-02-04
Week 5 | 2025-02-17 | Optimize Mobile UI | Ensure smooth survey experience on mobile | Pending
Week 5 | 2025-02-18 | Mobile Performance Testing | Check responsiveness on different devices | Pending
Week 5 | 2025-02-19 | Security Audit | Ensure no unauthorized data access | Pending
Week 5 | 2025-02-20 | Survey Performance Analytics | Track time taken per question | Pending
Week 5 | 2025-02-21 | Final UI Enhancements | Fix layout and responsiveness issues | Pending
Week 5 | 2025-02-22 | Test Large Surveys | Check system stability with large surveys | Pending
Week 5 | 2025-02-23 | Fix Major Bugs | Resolve issues found during testing | Pending
Week 6 | 2025-02-24 | Ensure Proper Survey Indexing | Optimize MongoDB indexes for faster queries | Pending
Week 6 | 2025-02-25 | Industry & Category Filtering | Allow analytics based on industry selection | Pending
Week 6 | 2025-02-26 | Optimize Email System | Ensure bulk emails don’t get marked as spam | Pending
Week 6 | 2025-02-27 | Final Survey Completion Reminders | Last-minute reminders to respondents | Pending
Week 6 | 2025-02-28 | Final Bug Fixes | Resolve remaining issues before feature freeze | Pending
Week 6 | 2025-03-01 | Feature Freeze | Lock features and start final testing | Pending
Week 6 | 2025-03-02 | Final Pre-March Testing | Ensure everything works smoothly | Pending
Week 7 | 2025-03-03 | Full System Testing | Check all workflows for stability | Pending
Week 7 | 2025-03-04 | Implement Extra Security Measures | Enhance access controls | Pending
Week 7 | 2025-03-05 | Final Review of Survey Workflows | Ensure smooth user journey | Pending
Week 7 | 2025-03-06 | Multi-User Testing | Check for performance issues with concurrent users | Pending
Week 7 | 2025-03-07 | Fix Load Testing Issues | Resolve any problems found | Pending
Week 7 | 2025-03-08 | Prepare for Beta Testing | Identify users for testing | Pending
Week 7 | 2025-03-09 | Feedback Collection Mechanism | Allow users to leave feedback on surveys | Pending
Week 7 | 2025-03-10 | Final Mobile Optimization | Ensure surveys work flawlessly on mobile | Pending
Week 7 | 2025-03-11 | Stress Testing | Test system under heavy load | Pending
Week 7 | 2025-03-12 | Security Patches | Implement final security improvements | Pending
Week 7 | 2025-03-13 | Final System Test Before Break | Ensure everything is ready | Pending
Week 7 | 2025-03-14 | Documentation | Write internal documentation for admins | Pending
Week 7 | 2025-03-15 | Final Bug Fixes & Feature Lock | Fix last-minute issues | Pending
Week 8 | 2025-03-30 | Post-Break System Review | Check for any unexpected issues | Pending
Week 8 | 2025-03-31 | Final Launch & Internal Rollout | Deploy system for usage | Pending